## Sheet1
Screen / functionality | html | php
environment |  | 8
Initial database |  | 8
Home | 10
settings Models (php) |  | 8
contact | 6 | 2
Image slider | 8 | 4
offers list | 10 | 2
columns module | 4 | 4
subscribtion | 10 | 20
signup | 12 | 8
su sumarry | 2 | 2
c signup | 2 | 1
login | 4 | 12
forgot pass | 2 | 4
tree menu | 10 | 8
dashboard | 24 | 20
sell art messiging | 30 | 40
permissions |  | 50
add offer | 20 | 30
offer preview | 10 | 10
offer details | 16 | 32
performance caching |  | 30
edit offer limitations | 20 | 50
Validations | 40 | 50
security |  | 40
wishlist | 10 | 20
favorites | 10 | 20
interesting | 8 | 20
search results | 8 | 4
seach module | 2 | 8
Advanced search module | 6 | 16
pagination | 1 | 8
editing custom list | 8 | 16
contact/repport | 8 | 8
forum custom - | 80 | 150
user edit | 12 | 8
upgrade subscription | 8 | 30
personal data | 8 | 20
authetication and roles | 6 | 24
statistics and repporting | 16 | 40
baickend User list / search screens | 16 | 10
transactions overview (list/details/edit/search) | 24 | 40
offers overview (list/details/edit/search) | 24 | 40
Users messages / comments overview | 24 | 40
favorites by user screens | 16 | 30
wishlist by user screens | 22 | 30
forum activities overview backend () | 40 | 60
settings admin | 30 | 40
partner management admin (all screens) | 40 | 60
performance / caching |  | 80
Stabilisation / bug fixing | 40 | 80
| 707 | 1345 | 2052
This is very rough estimation and estimation is based on PHP / MySQL technology using CodeIgniter as framework